## Sheet1
Day | Task No. | Description | Approximate duration | Dependencies
Day 1 | 1 | Identify the purpose of the project and the need within the analytics department | 6 hours | N/A
| 2 | Identify the scope of the project and the stakeholders | 5 hours | Task 1
| 3 | Identify what the fucntional requirements of this program are and how the game should work | 1 hour | Task 1
| 4 | Figure out the logic of the code by creating a flowchart of how data should be processed during the program | 15-30 minutes | Task 3
| 5 | Identify what platform the code will run on and which programming language | 1 hour | Task 3
Day 5 | 6 | Create first version of the program | 1-5 days | Task 5
| 7 | Test if the program can meet the functional requirements laid out by the task | 1-4 hours | Task 6
| 8 | Identify what the program failed to meet in the requirements and evaluate what else can be added | 1 hour | Task 7
| 9 | Develop another version of the code for noughts and crosses if needed | 1-5 days | Task 8
| 10 | Run another set of tests to see if the program meets the functional requirements | 1-4 hours | Task 9
Day 7 | 11 | Create documentation for the user on how to run the program and how to troubleshoot if there are issues | 1-2 days | Task 10
| 12 | Write up on evaluation and improvements that can be made for next time | 1-4 hours | Task 11
|  | Total duration approx. | Up to 13 days